## Summary
CXSH DDR4 3200 RevB
| Caterory | Total Test Case | WW27 Test Progress |  | WW28 Test Progress |  | WW29 Test Progress |  | WW30 Test Progress |  | WW31 Test Progress |  | WW32 Test Progress |  | Result |  |  |  |  | Pass Rate | Plan Schedule |  | Actual Schedule |  | Notes
|  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Pass | Fail | Block | Incomplete | Omitted |  | Start | End | Start | End
| Functional (1DPC) | 147 | 29 | 46 | 22 | 45 | 19 | 53 | 19 | 63 | 13 | 58 |  |  | 0 | 0 | 0 | 147 | 0 | 0%
| Functional (2DPC) | 127 | 21 | 52 | 21 | 49 | 17 | 48 | 17 | 54 | 13 | 51 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| DPMO | 6 | 1 | 6 | 1 | 5 | 1 | 4 | 1 | 3 | 1 | 2 |  |  | 6 | 0 | 0 | 0 | 0 | 100%
| PnP | 136 | 0 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 136 | 0 | 0%
| At Scale-Cluster Test | 86 | 0 | 0 | 0 | 0 | 22 | 22 | 21 | 21 | 22 | 21 | 21 | 22 | 0 | 0 | 0 | 86 | 0 | 0%
| HWV | 12 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 0 | 2 | 2 |  |  | 0 | 0 | 0 | 12 | 0 | 0%
Execution summary :
Sighting:
| id | Title | [18 empty] | Type | Status | exposure | Comments
| 15016494127 | [CXSH] [EMR][Cluster]Detected CE memory error on sh23l11002s0402.deacluster.intel.com during running dram-bank-stress | [18 empty] | presighting | open | 2-high | WW32.5: We can't see the issue after following WW32 2DPC workloads: virt-qemu. Will keep watching this issue during our following 2DPC test.
| 15016494329 | [CXSH] [EMR][Cluster]Detected CE memory error on sh23l11002s0502.deacluster.intel.com during running workload ive-vt-suite-hybriddense. | [18 empty] | presighting | open | 2-high | WW33.1: Trigger soft-PPR CE on E00A7E3B while running memory_margin/At Scale - AC Cycling SGX/TDX enabling 100 cycles/At Scale - coldboot Cycling SGX/TDX enabling 100 cycles
| 15016494720 | [CXSH] [EMR][Cluster]Detected CE memory error on sh23l11001s0102.deacluster.intel.com during running workload xprod-legacy. | [18 empty] | presighting | open | 2-high | WW33.1: We can't see the issue on this DIMM(E009B40D) after following 2DPC workloads: memory-margin.
| 15016544603 | [CXSH] [EMR][Cluster] Trigger PPR memory CE on sh23l11002s0502.deacluster.intel.com during testing coldboot 200 cycles. | [18 empty] | presighting | open | 2-high | WW33.1: E00AAF95 also trigger soft-PPR while running memory-margin workload. But can't trigger soft-PPR again after following 2DPC workloads: At Scale - warmboot Cycling SGX/TDX enabling 100 cycles/At Scale - AC Cycling SGX/TDX enabling 100 cycles/At Scale - coldboot Cycling SGX/TDX enabling 100 cycles.
| 15016570147 | [CXSH] [EMR][Cluster]Detected CE & UCE memory errors on sh23l11001s0102.deacluster.intel.com when running AMT_mlc_sandstone_combo. | [18 empty] | presighting | open | 2-high | WW33.1: We can't see this issue on this DIMM(E00A80D8) after following 2DPC workloads: memory-margin.
| 16025052059 | [CXSH] [EMR][Cluster]Detected 2 CE memory write errors on sh23l11002s0502.deacluster.intel.com when running Benchdnn. | [18 empty] | presighting | open | 2-high | WW33.1: We can't see memory write errors on this DIMM(E00A7E3B) after following 2DPC workloads: memory-margin/At Scale - warmboot Cycling SGX/TDX enabling 100 cycles/At Scale - AC Cycling SGX/TDX enabling 100 cycles/At Scale - coldboot Cycling SGX/TDX enabling 100 cycles.
| 16025052884 | [CXSH] [EMR][Cluster]Detected CE memory errors on sh23l11001s0102.deacluster.intel.com when running Resnet50 amx & Sandstone workload. | [18 empty] | presighting | open | 2-high | WW33.1: E00A5268 also trigger soft-PPR while running memory-margin workload.
| 18039530403 | [CXSH] [EMR][Cluster]OS not responding with SOL loop report memory errors on sh23l11001s0102.deacluster.intel.com when running xprod-legacy. | [18 empty] | presighting | open | 2-high--> 4-low | WW33.1: E00A5279 also trigger soft-PPR UCE while running memory-margin workload.
| 15016590658 | [CXSH] [EMR][Cluster]Single DIMM Memory Size downgrade from 64G to 32G in SMBIOS type 17 on sh23l11001s0102.deacluster.intel.com while running virt-qemu. | [18 empty] | presighting | open | 2-high | WW33.1: E00A5279 also trigger soft-PPR UCE while running memory-margin workload.
| 15016597753 | [CXSH] [EMR][Cluster] Detected CE & UCE on sh23l11001s0102.deacluster.intel.com while running virt-qemu | [18 empty] | presighting | open | 2-high | WW33.1: We can't see the issue on this DIMM(E00A7DA8) after following 2DPC workloads: memory margin/At Scale - AC Cycling SGX/TDX enabling 100 cycles/At Scale - coldboot Cycling SGX/TDX enabling 100 cycles/At Scale - warmboo Cycling SGX/TDX enabling 100 cycles.
| 15016500355 | [CXSH] [EMR][Cluster]IVE_Genie_SF-BoringSSL_Generic_numactl_node_1 error occurred once during running ive-sf-mixed-genie workload. | [18 empty] | presighting | open | 4-low | this issue was captured in CXSH 1DPC configuration. suggest to monitor it as regression check in CXSH 1DPC DIMM after we get new DIMM. but we can continue to put it with low priority
Complete
| id | Title | [18 empty] | Type | Status | exposure | Comments
| 15016388018 | [CXSH] [EMR][Cluster]Most of the latest IVE workloads image cannot be pulled on CXSH EMR SH cluster nodes | [18 empty] | sighting | complete | 2-high | Upgrade kubernetes to 1.26 and containerd to 1.7.0 solved this pull image issue. Also the blocked tests have been executed without any error during weekends in newly built k8s cluster.
| 15016489109 | [CXSH] [EMR][Cluster]WHEA: Detected Processor Error on sh23l11002s0102.deacluster.intel.com during running ptat-memory-write. | [18 empty] | presighting | complete | 4-low | Update WW31.1: Total 10 Nodes(include sh23l11002s0102 ), re-run the workload with the new container version "spiv-ipu-ptat-v1.1" during the 2DPC validation, CND.
Rejected
| id | Title | [18 empty] | Type | Status | exposure | closed_reason | Comments
| 15016465769 | [CXSH] [EMR]Appear mce error during DM_MEM_RANDOM_MIX_IIO-native-SNC_disabled test | [18 empty] | presighting | rejected | 2-high | cannot_reproduce
| 15016468506 | [CXSH] [EMR][Cluster]Serial log show ME status error during running warmboot & coldboot. | [18 empty] | presighting | rejected | 3-medium | test/test_env
| 15016472219 | [CXSH] [EMR][Cluster]BMC Critical Event PVNN_PCH_AUX sensor crossed a critical low threshold going low | [18 empty] | presighting | rejected | 3-medium | test/test_env
| 15016405063 | [Cluster][EMR]EMR machine reports an error “RuntimeError: Failed to set authorization level to Red for any device”when executing itp.unlock on pythonsv | [18 empty] | presighting | rejected | 2-high | test/test_env
| 15016425320 | [Cluster][EMR]The EMR machine reported "DDRT-Link-Failure-WA-Applied: err_ack_timer_limit = 0xF0" during the warm/cold boot test | [18 empty] | presighting | rejected | 3-medium | expected_behavior
| 15016521082 | [CXSH] [EMR][Cluster]BMC report "CPU2 memoery over temperature and being throttled" during running coldboot cycling w/ SGX/TDX enabled. | [18 empty] | presighting | rejected | 4-low | test/test_env | Reject the presighting since 1. issue can't reproduce for 2 days. 2. Event report as spike in between reboot cycles instead of real high temperature.
| 15016538041 | [CXSH] [EMR][Cluster]Dmidecode log is not as same as the last time on sh23l11002s0402.deacluster.intel.com. | [18 empty] | presighting | rejected | 4-low | expected_behavior | The following action can be take for the test script: Ignore the difference of table location which is expected. Even there's PSU infomation mismatch, that's directly between BMC and PSU with i2c connection, memory will not and shall not play a role here.
| 15016529043 | [CXSH] [EMR][Cluster]SUT shutdown and BMC show "CPU1 Thermal Trip and SSB Thermal trip" during running mesh-stress workload in sh23l11002s0402 node. | [18 empty] | presighting | rejected | 4-low | config_issue | WW32.2: We can't see the issue after following WW32 2DPC workloads: ive-vt-suite-autoreboots/ive-vt-suite-hybriddense/ive-vt-suite-hybridspread/ve-vt-suite-createteardown
| 15016466365 | [CXSH] [EMR][Cluster]Detected CE memory error on sh23l11002s0402.deacluster.intel.com during idle after running coldboot | [18 empty] | presighting | rejected | 2-high-->4-low | duplicate | Merge with 15016494127 since same error on same platform but different DIMM
| 15016537024 | [CXSH] [EMR][Cluster]Detected CE memory error on sh23l11002s0502.deacluster.intel.com when idle 1hrs20mins after testing warmboot 200 cycles. | [18 empty] | presighting | rejected | 2-high | duplicate | Merge with 15016494329 since 1.Same platform 2. Same error, CE happened after enter idle (self-refresh)
| 15016552109 | [CXSH] [EMR][Cluster]Detected CE memory error on sh23l11002s0402.deacluster.intel.com when idle 2hrs44mins after testing ac 200 cycles. | [18 empty] | presighting | open | 2-high-->4-low | duplicate | Merge with 15016494127 since 1. Same platform 2. Same CE error after idle (self-refresh)

## Config？
Host ID |  | Example C000 | sh14l02001s0501 | sh14l02001s0502 | sh14l02001s0601 | sh14l02001s0602 | sh14l02001s0701 | sh14l02001s0702 | sh14l02001s0801 | sh14l02001s0802 | sh14l02001s0901 | sh14l02001s0902 | sh14l02001s1001 | sh14l02001s1002 | sh14l02001s1101 | sh14l02001s1102 | sh14l02001s1201 | sh14l02001s1202 | sh14lva001s0301 | sh14lva001s0401
Test system ID |  | #Local049_CI | 801016 | 801017 | 801018 | 801019 | 801020 | 801021 | 801022 | 801023 | 801024 | 801025 | 801026 | 801027 | 801028 | 801029 | 801030 | 801031 | 798585 | 798586
SUT | CPU (Detail model info) | processor : 0 vendor_id : GenuineIntel cpu family : 6 model : 106 model name : Intel(R) Xeon(R) Platinum 8380 CPU @ 2.30GHz stepping : 6 microcode : 0xd0003c1 cpu MHz : 800.173 cache size : 61440 KB physical id : 0 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 49% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 NUMA node(s): 2 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation CPU family: 6 Model: 207 Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ Stepping: 2 CPU MHz: 1900.000 CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 Virtualization: VT-x L1d cache: 48K L1i cache: 32K L2 cache: 2048K L3 cache: 327680K NUMA node0 CPU(s): 0-63,128-191 NUMA node1 CPU(s): 64-127,192-255 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 50% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 49% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 48% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 Flags: fpu vme de pse tsc msr pae mce cx8 apic sep mtrr pge mca cmov pat pse36 clflush dts acpi mmx fx sr sse sse2 ss ht tm pbe syscall nx pdpe1gb rdtscp lm constant_tsc art arch_perfmon pebs bts re p_good nopl xtopology nonstop_tsc cpuid aperfmperf tsc_known_freq pni pclmulqdq dtes64 monitor ds_cpl vmx smx est tm2 ssse3 sdbg fma cx16 xtpr pdcm pcid dca sse4_1 sse4_2 x2apic movbe popcnt tsc_deadline_timer aes xsave avx f16c rdrand lahf_lm abm 3dnowprefetch cpuid_fault epb cat_l3 cat_l2 cdp_l3 invpcid_single cdp_l2 ssbd mba ibrs ibpb stibp ibrs_enhanced tpr_shadow vnmi flex priority ept vpid ept_ad fsgsbase tsc_adjust bmi1 hle avx2 smep bmi2 erms invpcid rtm cqm rdt_a avx512f avx512dq rdseed adx smap avx512ifma clflushopt clwb intel_pt avx512cd sha_ni avx512bw avx512vl xsaveopt xsavec xgetbv1 xsaves cqm_llc cqm_occup_llc cqm_mbm_total cqm_mbm_local split _lock_detect user_shstk avx_vnni avx512_bf16 wbnoinvd dtherm ida arat pln pts hwp hwp_act_windo w hwp_epp hwp_pkg_req avx512vbmi umip pku ospke waitpkg avx512_vbmi2 gfni vaes vpclmulqdq avx51 2_vnni avx512_bitalg tme avx512_vpopcntdq la57 rdpid bus_lock_detect cldemote movdiri movdir64b enqcmd fsrm md_clear serialize tsxldtrk pconfig arch_lbr ibt amx_bf16 avx512_fp16 amx_tile amx _int8 flush_l1d arch_capabilities Virtualization features: Virtualization: VT-x Caches (sum of all): L1d: 6 MiB (128 instances) L1i: 4 MiB (128 instances) L2: 256 MiB (128 instances) L3: 640 MiB (2 instances) NUMA: NUMA node(s): 2 NUMA node0 CPU(s): 0-63,128-191 NUMA node1 CPU(s): 64-127,192-255 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 224 On-line CPU(s) list: 0-223 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8570 BIOS Model name: INTEL(R) XEON(R) PLATINUM 8570 CPU @ 2.1GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 56 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 53% CPU max MHz: 4000.0000 CPU min MHz: 800.0000 BogoMIPS: 4200.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 49% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 | CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 50% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 Flags: fpu vme de pse tsc msr pae mce cx8 apic sep mtrr pge mca cmov pat pse36 clflush dts acpi mmx fx sr sse sse2 ss ht tm pbe syscall nx pdpe1gb rdtscp lm constant_tsc art arch_perfmon pebs bts re p_good nopl xtopology nonstop_tsc cpuid aperfmperf tsc_known_freq pni pclmulqdq dtes64 monitor ds_cpl vmx smx est tm2 ssse3 sdbg fma cx16 xtpr pdcm pcid dca sse4_1 sse4_2 x2apic movbe popcnt tsc_deadline_timer aes xsave avx f16c rdrand lahf_lm abm 3dnowprefetch cpuid_fault epb cat_l3 cat_l2 cdp_l3 invpcid_single cdp_l2 ssbd mba ibrs ibpb stibp ibrs_enhanced tpr_shadow vnmi flex priority ept vpid ept_ad fsgsbase tsc_adjust bmi1 hle avx2 smep bmi2 erms invpcid rtm cqm rdt_a avx512f avx512dq rdseed adx smap avx512ifma clflushopt clwb intel_pt avx512cd sha_ni avx512bw avx512vl xsaveopt xsavec xgetbv1 xsaves cqm_llc cqm_occup_llc cqm_mbm_total cqm_mbm_local split _lock_detect user_shstk avx_vnni avx512_bf16 wbnoinvd dtherm ida arat pln pts hwp hwp_act_windo w hwp_epp hwp_pkg_req avx512vbmi umip pku ospke waitpkg avx512_vbmi2 gfni vaes vpclmulqdq avx51 2_vnni avx512_bitalg tme avx512_vpopcntdq la57 rdpid bus_lock_detect cldemote movdiri movdir64b enqcmd fsrm md_clear serialize tsxldtrk pconfig arch_lbr ibt amx_bf16 avx512_fp16 amx_tile amx _int8 flush_l1d arch_capabilities Virtualization features: Virtualization: VT-x Caches (sum of all): L1d: 6 MiB (128 instances) L1i: 4 MiB (128 instances) L2: 256 MiB (128 instances) L3: 640 MiB (2 instances) NUMA: NUMA node(s): 2 NUMA node0 CPU(s): 0-63,128-191 NUMA node1 CPU(s): 64-127,192-255 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 NUMA node(s): 2 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation CPU family: 6 Model: 207 Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ Stepping: 2 CPU MHz: 1900.000 CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 Virtualization: VT-x L1d cache: 48K L1i cache: 32K L2 cache: 2048K L3 cache: 327680K NUMA node0 CPU(s): 0-63,128-191 NUMA node1 CPU(s): 64-127,192-255 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 224 On-line CPU(s) list: 0-223 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8570 BIOS Model name: INTEL(R) XEON(R) PLATINUM 8570 CPU @ 2.1GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 56 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 52% CPU max MHz: 4000.0000 CPU min MHz: 800.0000 BogoMIPS: 4200.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 NUMA node(s): 2 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation CPU family: 6 Model: 207 Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ Stepping: 2 CPU MHz: 1900.000 CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 Virtualization: VT-x L1d cache: 48K L1i cache: 32K L2 cache: 2048K L3 cache: 327680K NUMA node0 CPU(s): 0-63,128-191 NUMA node1 CPU(s): 64-127,192-255 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 NUMA node(s): 2 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation CPU family: 6 Model: 207 Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ Stepping: 2 CPU MHz: 1900.000 CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 Virtualization: VT-x L1d cache: 48K L1i cache: 32K L2 cache: 2048K L3 cache: 327680K NUMA node0 CPU(s): 0-63,128-191 NUMA node1 CPU(s): 64-127,192-255 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 48% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 48% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 224 On-line CPU(s) list: 0-223 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8570 BIOS Model name: INTEL(R) XEON(R) PLATINUM 8570 CPU @ 2.1GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 56 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 61% CPU max MHz: 4000.0000 CPU min MHz: 800.0000 BogoMIPS: 4200.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 256 On-line CPU(s) list: 0-255 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8592+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8592+ CPU @ 1.9GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 64 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 49% CPU max MHz: 3900.0000 CPU min MHz: 800.0000 BogoMIPS: 3800.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 192 On-line CPU(s) list: 0-191 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8568Y+ BIOS Model name: INTEL(R) XEON(R) PLATINUM 8568Y+ CPU @ 2.3GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 48 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 58% CPU max MHz: 4000.0000 CPU min MHz: 800.0000 BogoMIPS: 4600.00 | Architecture: x86_64 CPU op-mode(s): 32-bit, 64-bit Address sizes: 52 bits physical, 57 bits virtual Byte Order: Little Endian CPU(s): 224 On-line CPU(s) list: 0-223 Vendor ID: GenuineIntel BIOS Vendor ID: Intel(R) Corporation Model name: INTEL(R) XEON(R) PLATINUM 8570 BIOS Model name: INTEL(R) XEON(R) PLATINUM 8570 CPU @ 2.1GHz BIOS CPU family: 179 CPU family: 6 Model: 207 Thread(s) per core: 2 Core(s) per socket: 56 Socket(s): 2 Stepping: 2 CPU(s) scaling MHz: 53% CPU max MHz: 4000.0000 CPU min MHz: 800.0000 BogoMIPS: 4200.00
| OS | redhat 8.2 & Windows | CentOS Stream 9(Kernel 6.2.19) | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 8 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | CentOS Stream 9 | Red Hat Enterprise Linux 9.2 (Plow)
| CPU QDF code | SRKHC | Q3W7 | Q3W7 | Q3W7 | Q3W7 | Q3W7 | Q3W7 | Q3W7 | Q3W7 | Q3W5 | Q3W5 | Q3W7 | Q3W7 | Q3W7 | Q3W7 | Q3W5 | Q3W7 | Q3W4 | Q3W4
| PCH QDF code | SRH58
| IFWI version | WLYDCRB.GOP.WR.64.2023.33.1.02.1216_0030.P39_P003c1_LBG_SPS_ICX_Production.bin | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159 | EGSDCRB1.SYS.0109.D34.2406071159
| BMC version | OBMC-wht-1.01-75-g3685a0-31e5d79 | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b-pfr-full.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b.ROM | OBMC-egs-1.19-0-gd25ec8-d44106b.ROM
| CPLD version | cpld_pfr_627_4 | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof | ac_rp_fab3_SecondaryFpga_0vC_Official.pof pfr_b659.4.pof
BIOS cap(Option)
SPS Cap(Option)
PMEM FW(Option)
| DIMM | DDR4 Micron/Intel 3200MT/s SR*4 16*16GB/256GB | CX 64G*32 | 16GB *1 | 16GB * 2 | CX 64GB * 32 | CX 64GB * 16 | 16GB * 2 | CX 64GB * 32 | CX 64GB * 16 | 16GB * 2 | CX 64GB * 32 | CX 64GB * 32 | CX 64GB * 16 | CX 64GB * 16 | 16GB * 2 | CX 64GB * 16 | CX 64GB * 16 |  | 16GB * 2
| Disk Drives | 480GB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 2 TB | 14.6TB | 400 GB
| VROC key (Yes or No) | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no
| MB NIC ports | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
| Network Card (Detail model info) | Yes | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no
| PCIe Card (Detail module ) |  | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no
| ITP (Yes or No) | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
| Banino/DediProg /EM100/Y2prog to CPLD pin | Yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
| Banino/DediProg /EM100/Y2prog to BIOS pin | No | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
| RSC2 | Yes | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no | no
| USB port | Yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
| BIOS serial cable (Yes or No) | Yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
| BMC serial cable (Yes or No) | Yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
Host | OS | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows | windows
| pythonsv | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
| cscript | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Yes
No
Done
Not Started
WIP
Pre-condition | kernel log open |  | yes |  |  |  | yes |  |  | yes |  |  | yes | yes | yes |  | yes
| Owner |  | ZhouJun |  |  | Xingfu | Dongwang |  | WangXu | LiDongwang |  | LiuXingfu | yuanwenliang | Shengqing | ZhouJun |  | Shengqing
| PN |  | CXMR4E464R8AS-CB1C

## Cluster_Config？
Advanced system configuration | sh23l11001s0102.deacluster.intel.com | Advanced system configuration | sh23l11002s0102.deacluster.intel.com
Ingredient | HW Version Details | Ingredient | HW Version Details
Platform | EMR 2sockets 56core/socket | Platform | EMR 2sockets 56core/socket
CPU ID | 06-cf-02 | CPU ID | 06-cf-02
Production ID | INTEL(R) XEON(R) PLATINUM 8592+ | Production ID | INTEL(R) XEON(R) PLATINUM 8592+
CPU 0/1 | Q3W7 | CPU 0/1 | Q3W7
Base Board | Archer City, PBA:K46386-408 | Base Board | Archer City, PBA:K46386-408
DDR5 memory | CXSH DDR5 5600MT/s 64GB*16 | DDR5 memory | CXSH DDR5 5600MT/s 64GB*16
PCH | QY0U | PCH | RLGE
TDP | 350W | TDP | 350W
Storage | INTEL SSDSC2KB019T7 1.7T BTYG02110A8Q1P9DGN | Storage | INTEL SSDSC2KG019T8 1.7T
NIC | Intel Corporation Ethernet Controller I225-LM (rev 03) | NIC | Intel Corporation Ethernet Controller I225-LM (rev 03)
| SW Version Details |  | SW Version Details
OS | CentOS Stream release 9 | OS | CentOS Stream release 9
OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64 | OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64
BIOS | EGSDCRB1.SYS.0109.D34.2406071159 | BIOS | EGSDCRB1.SYS.0109.D34.2406071159
BMC | egs-1.19-0-gd25ec8-d44106b | BMC | egs-1.19-0-gd25ec8-d44106b
CPLD | 58.0-2.0 | CPLD | 58.0-2.0
ME | 6.1.4.047.0 | ME | 6.1.4.047.0
MCU | 0x21000281 | MCU | 0x21000281
Configuration | sh23l11002s0202.deacluster.intel.com | Advanced system configuration | sh23l11002s0302.deacluster.intel.com
Ingredient | HW Version Details | Ingredient | HW Version Details
Platform | EMR 2sockets 56core/socket | Platform | EMR 2sockets 56core/socket
CPU ID | 06-cf-02 | CPU ID | 06-cf-02
Production ID | INTEL(R) XEON(R) PLATINUM 8570 | Production ID | INTEL(R) XEON(R) PLATINUM 8570
CPU 0/1 | Q3W5 | CPU 0/1 | Q3W5
Base Board | Archer City, PBA:K46386-408 | Base Board | Archer City, PBA:K46386-408
DDR5 memory | Hynix DDR5 5600MT/s 32GB*32 | DDR5 memory | CXSH DDR5 5600MT/s 64GB*16
PCH | RLGE | PCH | RLGE
TDP | 350W | TDP | 350W
Storage | INTEL SSDSC2KG019T8 1.7T BTYG02050CEU1P9DGN | Storage | INTEL SSDSC2KG019T8 1.7T BTYG020509ZV1P9DGN
NIC | Intel Corporation Ethernet Controller I225-LM (rev 03) | NIC | Intel Corporation Ethernet Controller I225-LM (rev 03)
| SW Version Details |  | SW Version Details
OS | CentOS Stream release 9 | OS | CentOS Stream release 9
OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64 | OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64
BIOS | EGSDREL1.SYS.0109.D34.2402031435 | BIOS | EGSDCRB1.SYS.0109.D34.2406071159
BMC | egs-1.19-0-gd25ec8-d44106b | BMC | egs-1.19-0-gd25ec8-d44106b
CPLD | 58.0-2.0 | CPLD | 58.0-2.0
ME | 6.1.4.047.0 | ME | 6.1.4.047.0
MCU | 0xa1000230 | MCU | 0x21000281
Advanced system configuration | sh23l11002s0402.deacluster.intel.com | Advanced system configuration | sh23l11002s0502.deacluster.intel.com
Ingredient | HW Version Details | Ingredient | HW Version Details
Platform | EMR 2sockets 56core/socket | Platform | EMR 2sockets 56core/socket
CPU ID | 06-cf-02 | CPU ID | 06-cf-02
Production ID | INTEL(R) XEON(R) PLATINUM 8570 | Production ID | INTEL(R) XEON(R) PLATINUM 8570
CPU 0/1 | Q3W5 | CPU 0/1 | Q3W5
Base Board | Archer City, PBA:K46386-408 | Base Board | Archer City, PBA:K46386-408
DDR5 memory | CXSH DDR5 5600MT/s 64GB*16 | DDR5 memory | CXSH DDR5 5600MT/s 64GB*16
PCH | RLGE | PCH | RLGE
TDP | 350W | TDP | 350W
Storage | INTEL SSDSC2KB019T7 1.7T PHYS728501KU1P9DGN | Storage | INTEL SSDSC2KG019T8 1.7T BTYG02110CR11P9DGN
NIC | Intel Corporation Ethernet Controller I225-LM (rev 03) | NIC | Intel Corporation Ethernet Controller I225-LM (rev 03)
| SW Version Details |  | SW Version Details
OS | CentOS Stream release 9 | OS | CentOS Stream release 9
OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64 | OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64
BIOS | EGSDCRB1.SYS.0109.D34.2406071159 | BIOS | EGSDCRB1.SYS.0109.D34.2406071159
BMC | egs-1.19-0-gd25ec8-d44106b | BMC | egs-1.19-0-gd25ec8-d44106b
CPLD | 58.0-2.0 | CPLD | 58.0-2.0
ME | 6.1.4.047.0 | ME | 6.1.4.047.0
MCU | 0x21000281 | MCU | 0x21000281
Advanced system configuration | sh23l11002s0602.deacluster.intel.com | Advanced system configuration | sh23l11002s0702.deacluster.intel.com
Ingredient | HW Version Details | Ingredient | HW Version Details
Platform | EMR 2sockets 56core/socket | Platform | EMR 2sockets 64core/socket
CPU ID | 06-cf-02 | CPU ID | 06-cf-02
Production ID | INTEL(R) XEON(R) PLATINUM 8570 | Production ID | INTEL(R) XEON(R) PLATINUM 8592+
CPU 0/1 | Q3W5 | CPU 0/1 | Q3W7
Base Board | Archer City, PBA:K46386-408 | Base Board | Intel 4U Closed Chassis Archer City Server M16145-003, PBA K46386-407
DDR5 memory | Hynix DDR5 5600MT/s 32GB*32 | DDR5 memory | CXSH DDR5 5600MT/s 64GB*16
PCH | QY0U | PCH | RLGE
TDP | 350W | TDP | 350W
Storage | INTEL SSDSC2KG019T8 1.7T BTYG020505AU1P9DGN | Storage | SAMSUNG MZWLO1T9HCJR-00A07 1.7T S795NC0X100315
NIC | Intel Corporation Ethernet Controller I225-LM (rev 03) | NIC | Intel Corporation Ethernet Controller I225-LM (rev 03)
| SW Version Details |  | SW Version Details
OS | CentOS Stream release 9 | OS | CentOS Stream release 9
OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64 | OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64
BIOS | EGSDCRB1.SYS.0109.D34.2406071159 | BIOS | EGSDCRB1.SYS.0109.D34.2406071159
BMC | egs-1.19-0-gd25ec8-d44106b | BMC | egs-1.19-0-gd25ec8-d44106b
CPLD | 58.0-2.0 | CPLD | 58.0-2.0
ME | 6.1.4.047.0 | ME | 6.1.4.047.0
MCU | 0x21000281 | MCU | 0x21000281
Advanced system configuration | r006s001.sh23lrasp1 | Advanced system configuration | r006s002.sh23lrasp1
Ingredient | HW Version Details | Ingredient | HW Version Details
Platform | EMR 2sockets 64core/socket | Platform | EMR 2sockets 64core/socket
CPU ID | 06-cf-02 | CPU ID | 06-cf-02
Production ID | INTEL(R) XEON(R) PLATINUM 8570 | Production ID | INTEL(R) XEON(R) PLATINUM 8570
CPU 0/1 | Q3W5 | CPU 0/1 | Q3W5
Base Board | Archer City, PBA:K46386-409 | Base Board | Archer City, PBA:K46386-409
DDR5 memory | Hynix DDR5 5600MT/s 32GB*32 | DDR5 memory | Hynix DDR5 5600MT/s 32GB*32
PCH |  | PCH
TDP | 350W | TDP | 350W
Storage | SAMSUNG MZWLO1T9HCJR-00B5C 1.7T S6ZYNG0T600367 | Storage | SAMSUNG MZWLO1T9HCJR-00B5C 1.7T S6ZYNG0T600425
NIC | Intel Corporation Ethernet Controller I225-LM (rev 03) | NIC | Intel Corporation Ethernet Controller I225-LM (rev 03) Intel Corporation 82599ES 10-Gigabit SFI/SFP+ Network Connection (rev 01) Intel Corporation 82599ES 10-Gigabit SFI/SFP+ Network Connection (rev 01)
| SW Version Details |  | SW Version Details
OS | CentOS Stream release 9 | OS | CentOS Stream release 9
OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64 | OS Kernel | 6.2.0-emr.bkc.6.2.19.2.52.x86_64
BIOS | EGSDCRB1.SYS.0109.D34.2406071159 | BIOS | EGSDCRB1.SYS.0109.D34.2406071159
BMC | egs-1.19-0-gd25ec8-d44106b | BMC | egs-1.19-0-gd25ec8-d44106b
CPLD | 58.0-2.0 | CPLD | 58.0-2.0
ME | 6.1.4.047.0 | ME | 6.1.4.047.0
MCU | 0x21000281 | MCU | 0x21000281

## Functional (overall)
New ID | New Title | Original HSDES ID | Domain | Case title | Status | DTAF/iAuto | 1DPC | 2DPC
15016656293 | MEM_MEMTEST86 | 18018171911 | MEM-Stress | PI_Memory_DDR4_Memtest86Stress_L | auto | iAuto | Y | Y
15016656334 | MEM_2xREFRESH_STRESSAPP | 15012721147 | MEM-Thermal | MEM - Stressapp with 2x Refresh Enabled/Disabled_1DPC_or_2DPC (Linux) | auto | iAuto | Y | Y
16025222171 | MEM_PRIME95_SNC_enabled | 15013004990 | MEM-Stress | PIV_Memory_SNC2_Prime95_1DPC_or_2DPC_L | auto | iAuto | Y | Y
16025222192 | MEM_PRIME95_SNC_disabled | 15012993465 | MEM-Stress | PIV_Memory_Hemi_Prime95_1DPC_or_2DPC_L | auto | iAuto | Y | Y
16025222219 | MEM_ilVSS_SNC_disabled | 15013005170 | MEM-Stress | PIV_Memory_Hemi_ilVSS_1DPC_or_2DPC_L | auto | iAuto | Y | Y
16025222250 | MEM_ilVSS_SNC_enabled | 15012993537 | MEM-Stress | PIV_Memory_SNC2_ilVSS_1DPC_or_2DPC_L | auto | iAuto | Y | Y
16025222278 | MEM_MLC_SNC_disabled | 15010580156 | MEM-Stress | PIV_Memory_Hemi_MLC_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016661169 | MEM_MLC_SNC_enabled | 15010580460 | MEM-Stress | PIV_Memory_SNC2_MLC_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016661346 | MEM_STRESSAPP_SNC_disabled | 15012721042 | MEM-Stress | PIV_Memory_SNC2_Stressapp_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016661219 | MEM_STRESSAPP_SNC_enabled | 15010581424 | MEM-Stress | PIV_Memory_Hemi_Stressapp_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016662134 | MEM_AC_CYCLE_FAST_BOOT_enabled | 15010591929 | MEM-Powercycle | PIV_IPU_AC_Cycle_Fastcoldboot_Enabled_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016662739 | MEM_AC_CYCLE_FAST_BOOT_disabled | 15010592010 | MEM-Powercycle | PIV_IPU_AC_Cycle_Fastcoldboot_Disabled_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016662178 | MEM_OS_Shutdown_Cycle_FAST_BOOT_enabled | 15010592012 | MEM-Powercycle | PIV_IPU_OS_Shutdown_Cycle_Fastcoldboot_Enabled_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016662191 | MEM_OS_Shutdown_Cycle_FAST_BOOT_disabled | 15010592028 | MEM-Powercycle | PIV_IPU_OS_Shutdown_Cycle_Fastcoldboot_Disabled_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016662214 | MEM_OS_Reboot_Cycle_FAST_BOOT_enabled | 15010592059 | MEM-Powercycle | PIV_IPU_OS_Reboot_Cycle_Fastcoldboot_Enabled_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016662238 | MEM_OS_Reboot_Cycle_FAST_BOOT_disabled | 15010592076 | MEM-Powercycle | PIV_IPU_OS_Reboot_Cycle_Fastcoldboot_Disabled_1DPC_or_2DPC_L | auto | iAuto | Y | Y
15016655034 | MEM_EV_ICX_DDR4_RMT_FAST_COLD_RESET_2933 | NEW | MEM-RMT |  | New | Manual | Y | Y
15016655118 | MEM_EV_ICX_DDR4_RMT_SLOW_COLD_RESET_2933 | NEW | MEM-RMT |  | New | Manual | Y | Y
15016655151 | MEM_EV_ICX_DDR4_RMT_FAST_COLD_RESET_3200 | NEW | MEM-RMT |  | New | Manual | Y | Y
15016655448 | MEM_EV_ICX_DDR4_RMT_SLOW_WARM_RESET_2933 | NEW | MEM-RMT |  | New | Manual | Y | Y
15016655687 | MEM_EV_ICX_DDR4_RMT_SLOW_WARM_RESET_3200 | NEW | MEM-RMT |  | New | Manual | Y | Y
22016633911 | MEM_EV_ICX_DDR4_RMT_SLOW_COLD_RESET_3200 | NEW | MEM-RMT |  | New | Manual | Y | Y
15016668008 | MEM_AMT_ON_GOODDIMM | 15012405943 | MEM-AMT | PIV_IPU_Pistachio_AMT_Vendor_GoodDIMM_AutoSerial | Manual | Manual | Y | Y
15016669187 | MEM_OS_IDLE-SNC_enabled | NEW | MEM-IDLE |  | Manual | Manual | Y | Y
15016669239 | MEM_OS_IDLE--SNC_disabled | NEW | MEM-IDLE |  | Manual | Manual | Y | Y
15016661662 | RAS_EINJ_MEM_UNCORRECTABLE_NONFATAL | 18018170016 | RAS | PI_RAS_einj_mem_uncorrectable_nonfatal | auto | iAuto | Y | Y
15016662626 | RAS_EINJ_MEM_CORRECTABLE | 18018170013 | RAS | PI_RAS_MEM_einj_mem_correctable | auto | iAuto | Y | Y
15016662875 | RAS_EINJ_MEM_UNCORRECTABLE_FATAL | 18018170018 | RAS | PI_RAS_einj_mem_uncorrectable_fatal | auto | iAuto | Y | Y
15016662909 | RAS_PCLS_PCLSEN_SBCE_SAMECH_INDIVIDUALCACHELINE_L | 15010738897 | RAS | IPU_RAS_PCLS_PclsEn_SBCE_SameCH_IndividualCacheLine_L | auto | iAuto | Y | Y
15016662935 | RAS_MEMORY MIRRORING - INTRA IMC_CORRERR_L | 18018170036 | RAS | PI_RAS_Memory Mirroring - Intra iMC_correrr_L | auto | iAuto | Y | Y
15016661598 | RAS_PCLS_PCLSDIS_SWERRTHEN_L | 15010785545 | RAS | IPU_RAS_PCLS_PclsDis_SwErrThEn_L | auto | iAuto | Y | Y
15016663509 | RAS_PCLS_PCLSDIS_SWERRTHDIS_L | 15010785902 | RAS | IPU_RAS_PCLS_PclsDis_SwErrThDis_L | auto | iAuto | Y | Y
15016663636 | RAS_PISTACHIO_PPR_UCE_UCR_CE_PATROLSCRUB_L | 18018168556 | RAS | PIV_IPU_Pistachio_PPR_UCE_UCR_CE_PatrolScrub_L | auto | iAuto | Y | Y
15016663664 | RAS_PISTACHIO_AMT_VENDOR_ITP_MEMTESTFAILURE_SPPR_BDAT | 15012479005 | RAS | PIV_IPU_Pistachio_AMT_Vendor_ITP_MemTestFailure_sPPR_BDAT_whitley | auto | iAuto | Y | Y
15016663684 | RAS_PPRRECORDED_UC_ALL_CHANNEL_DIMM_ALL_RANK | 15012478975 | RAS | PIV_IPU_PPRrecorded_UC_all_channel_DIMM_all_Rank | auto | iAuto | Y | Y
15016663692 | RAS_PISTACHIO_PPR_UCE_SURPRISE_RESET_L | 18018138512 | RAS | PIV_IPU_Pistachio_PPR_UCE_Surprise_Reset_L | auto | iAuto | Y | Y
15016670774 | Powermanagement_HWP_Native_L | 15011799624 | PM-P state | SPIV_IPU_Powermanagement_HWP_Native_L | auto | iAuto | Y | Y
15016670815 | Powermanagement_HWP_OOB_L | 15011943770 | PM-OOB | PIV_IPU_Powermanagement_HWP_OOB_L | auto | iAuto | Y | Y
15016670821 | Powermanagement_PC6_Enable_Idle_SoCwatch_L | 15011800314 | PM-Package C6/Core C6 | SPIV_IPU_Powermanagement_PC6_Enable_Idle_SoCwatch_L | auto | iAuto | Y | Y
15016670844 | Powermanagement_Power_Cstate_Disable_idle_AND_stress_hybrid_socwatch_L | 15011844441 | PM-Stress-Package C0/Core C0,C1E | SPIV_IPU_Powermanagement_Power_Cstate_Disable_idle_AND_stress_hybrid_socwatch_L | auto | iAuto | Y | Y
15016670861 | Powermanagement_Power_Cstate_Enable_idle_AND_stress_hybrid_socwatch_L | 15011838225 | PM-Stress-Package C0,C1,C6/Core C0,C6 | SPIV_IPU_Powermanagement_Power_Cstate_Enable_idle_AND_stress_hybrid_socwatch_L | auto | iAuto | Y | Y
15016670880 | Powermanagement_Turbo_State_Disable_Stress_SoCwatch_L | 15011803618 | PM-Stress-Turbo Disable | PIV_IPU_Powermanagement_Turbo_State_Disable_Stress_SoCwatch_L | auto | iAuto | Y | Y
15016670919 | Powermanagement_UFS_L | 15011843343 | PM-UFS | SPIV_IPU_Powermanagement_UFS_L | auto | iAuto | Y | Y
15016670940 | Powermanagement_Turbo_State_enable_SoCwatch_L | 15011750403 | PM-stress-Turbo Enable | SPIV_IPU_Powermanagement_Turbo_State_enable_SoCwatch_L | auto | iAuto | Y | Y

## Functional (1DPC)
ID | Title | Category | Priority | A:1DPC | Test Schedule | Test Result | Sighting | Test owner | Test Duration | Test Date | Test Config | Comment
15016661662 | RAS_EINJ_MEM_UNCORRECTABLE_NONFATAL | RAS | P1 | Y |  | WIP |  |  |  | 2024-09-03 | SHIPUNUC048
15016662626 | RAS_EINJ_MEM_CORRECTABLE | RAS | P1 | Y
15016662875 | RAS_EINJ_MEM_UNCORRECTABLE_FATAL | RAS | P1 | Y
15016662909 | RAS_PCLS_PCLSEN_SBCE_SAMECH_INDIVIDUALCACHELINE_L | RAS | P1 | Y
15016662935 | RAS_MEMORY MIRRORING - INTRA IMC_CORRERR_L | RAS | P1 | Y
15016661598 | RAS_PCLS_PCLSDIS_SWERRTHEN_L | RAS | P1 | Y
15016663509 | RAS_PCLS_PCLSDIS_SWERRTHDIS_L | RAS | P1 | Y
15016663636 | RAS_PISTACHIO_PPR_UCE_UCR_CE_PATROLSCRUB_L | RAS | P1 | Y
15016663664 | RAS_PISTACHIO_AMT_VENDOR_ITP_MEMTESTFAILURE_SPPR_BDAT | RAS | P1 | Y
15016663684 | RAS_PPRRECORDED_UC_ALL_CHANNEL_DIMM_ALL_RANK | RAS | P1 | Y
15016663692 | RAS_PISTACHIO_PPR_UCE_SURPRISE_RESET_L | RAS | P1 | Y

## Functional (2DPC)
ID | Title | Category | Priority | A:1DPC | Test Schedule | Test Result | Sighting | Test owner | Test Duration | Test Date | Test Config | Comment
15016656293 | MEM_MEMTEST86 | MEM-Stress | P1 | Y
15016656334 | MEM_2xREFRESH_STRESSAPP | MEM-Thermal | P1 | Y
16025222171 | MEM_PRIME95_SNC_enabled | MEM-Stress | P1 | Y
16025222192 | MEM_PRIME95_SNC_disabled | MEM-Stress | P1 | Y
16025222219 | MEM_ilVSS_SNC_disabled | MEM-Stress | P1 | Y
16025222250 | MEM_ilVSS_SNC_enabled | MEM-Stress | P1 | Y
16025222278 | MEM_MLC_SNC_disabled | MEM-Stress | P1 | Y
16025222250 | MEM_ilVSS_SNC_enabled | MEM-Stress | P1 | Y
15016661346 | MEM_STRESSAPP_SNC_disabled | MEM-Stress | P1 | Y
15016661219 | MEM_STRESSAPP_SNC_enabled | MEM-Stress | P1 | Y
15016662134 | MEM_AC_CYCLE_FAST_BOOT_enabled | MEM-Powercycle | P1 | Y
15016662739 | MEM_AC_CYCLE_FAST_BOOT_disabled | MEM-Powercycle | P1 | Y
15016662178 | MEM_OS_Shutdown_Cycle_FAST_BOOT_enabled | MEM-Powercycle | P1 | Y
15016662191 | MEM_OS_Shutdown_Cycle_FAST_BOOT_disabled | MEM-Powercycle | P1 | Y
15016662214 | MEM_OS_Reboot_Cycle_FAST_BOOT_enabled | MEM-Powercycle | P1 | Y
15016662238 | MEM_OS_Reboot_Cycle_FAST_BOOT_disabled | MEM-Powercycle | P1 | Y
15016655034 | MEM_EV_ICX_DDR4_RMT_FAST_COLD_RESET_2933 | MEM-RMT | P1 | Y
15016655118 | MEM_EV_ICX_DDR4_RMT_SLOW_COLD_RESET_2933 | MEM-RMT | P1 | Y
15016655151 | MEM_EV_ICX_DDR4_RMT_FAST_COLD_RESET_3200 | MEM-RMT | P1 | Y
15016655448 | MEM_EV_ICX_DDR4_RMT_SLOW_WARM_RESET_2933 | MEM-RMT | P1 | Y
15016655687 | MEM_EV_ICX_DDR4_RMT_SLOW_WARM_RESET_3200 | MEM-RMT | P1 | Y
22016633911 | MEM_EV_ICX_DDR4_RMT_SLOW_COLD_RESET_3200 | MEM-RMT | P1 | Y
15016668008 | MEM_AMT_ON_GOODDIMM | MEM-AMT | P1 | Y
15016669187 | MEM_OS_IDLE-SNC_enabled | MEM-IDLE | P1 | Y
15016669239 | MEM_OS_IDLE--SNC_disabled | MEM-IDLE | P1 | Y
15016661662 | RAS_EINJ_MEM_UNCORRECTABLE_NONFATAL | RAS | P1 | Y
15016662626 | RAS_EINJ_MEM_CORRECTABLE | RAS | P1 | Y
15016662875 | RAS_EINJ_MEM_UNCORRECTABLE_FATAL | RAS | P1 | Y
15016662909 | RAS_PCLS_PCLSEN_SBCE_SAMECH_INDIVIDUALCACHELINE_L | RAS | P1 | Y
15016662935 | RAS_MEMORY MIRRORING - INTRA IMC_CORRERR_L | RAS | P1 | Y
15016661598 | RAS_PCLS_PCLSDIS_SWERRTHEN_L | RAS | P1 | Y
15016663509 | RAS_PCLS_PCLSDIS_SWERRTHDIS_L | RAS | P1 | Y
15016663636 | RAS_PISTACHIO_PPR_UCE_UCR_CE_PATROLSCRUB_L | RAS | P1 | Y
15016663664 | RAS_PISTACHIO_AMT_VENDOR_ITP_MEMTESTFAILURE_SPPR_BDAT | RAS | P1 | Y
15016663684 | RAS_PPRRECORDED_UC_ALL_CHANNEL_DIMM_ALL_RANK | RAS | P1 | Y
15016663692 | RAS_PISTACHIO_PPR_UCE_SURPRISE_RESET_L | RAS | P1 | Y
15016670774 | Powermanagement_HWP_Native_L | PM-P state | P1 | Y
15016670815 | Powermanagement_HWP_OOB_L | PM-OOB | P1 | Y
15016670821 | Powermanagement_PC6_Enable_Idle_SoCwatch_L | PM-Package C6/Core C6 | P1 | Y
15016670844 | Powermanagement_Power_Cstate_Disable_idle_AND_stress_hybrid_socwatch_L | PM-Stress-Package C0/Core C0,C1E | P1 | Y
15016670861 | Powermanagement_Power_Cstate_Enable_idle_AND_stress_hybrid_socwatch_L | PM-Stress-Package C0,C1,C6/Core C0,C6 | P1 | Y
15016670880 | Powermanagement_Turbo_State_Disable_Stress_SoCwatch_L | PM-Stress-Turbo Disable | P1 | Y
15016670919 | Powermanagement_UFS_L | PM-UFS | P1 | Y
15016670940 | Powermanagement_Turbo_State_enable_SoCwatch_L | PM-stress-Turbo Enable | P1 | Y

## PnP
test case | Test Schedule | Test Result | Sighting | Test owner | Test Duration | Test Date | Test Config | Golden_Sample_H-64GB |  |  |  |  | CXSH SKU1 64GB RevA |  |  |  |  | difference | Comment
[8 empty] | iteration 1 | iteration 2 | iteration 3 | median | %CV | iteration 1 | iteration 2 | iteration 3 | median | %CV
MLC local socket local cluster memory latency
MLC remote socket memory latency
MLC local socket local cluster memory latency random
MLC remote socket memory latency random
MLC local socket remote cluster memory latency
MLC local socket remote cluster memory latency random
MLC Peak Bandwidth - 1TPC NUMA0 100R
MLC Peak Bandwidth - 1TPC NUMA1 100R
MLC Peak Bandwidth - 1TPC Socket 0 100R
MLC Peak Bandwidth - 1TPC Socket 1 100R
MLC Peak Bandwidth - 1TPC All Sockets 100R
MLC Peak Bandwidth - 1TPC All Sockets 2R1W RFO
MLC Peak Bandwidth - 1TPC All Sockets 3R1W RFO
MLC Peak Bandwidth - 1TPC All Sockets 3R2W RFO
MLC Peak Bandwidth - 1TPC All Sockets 1R1W RFO
MLC Peak Bandwidth - 1TPC All Sockets 100W
MLC Peak Bandwidth - 1TPC All Sockets 2R1W NTW
MLC Peak Bandwidth - 1TPC All Sockets 1R1W NTW
MLC Peak Bandwidth - 1TPC All Sockets 3R1W NTW
MLC Peak Bandwidth - 1TPC All Sockets 2R1W NTW (triad like)
MLC Remote Socket Peak bandwidth 1TPC - 100R
MLC Remote Socket Peak bandwidth 1TPC - 2R1W RFO
MLC Remote Socket Peak bandwidth 1TPC - 3R1W RFO
MLC Remote Socket Peak bandwidth 1TPC - 3R2W RFO
MLC Remote Socket Peak bandwidth 1TPC - 1R1W RFO
MLC Remote Socket Peak bandwidth 1TPC - 100W
MLC Remote Socket Peak bandwidth 1TPC - 2R1W NTW
MLC Remote Socket Peak bandwidth 1TPC - 1R1W NTW
MLC Remote Socket Peak bandwidth 1TPC - 3R1W NTW
MLC Remote Socket Peak bandwidth 1TPC - 2R1W NTW (triad like)
MLC Remote Socket Peak bandwidth Reverse 1TPC - 100R
MLC Remote Socket Peak bandwidth Reverse 1TPC - 2R1W RFO
MLC Remote Socket Peak bandwidth Reverse 1TPC - 3R1W RFO
MLC Remote Socket Peak bandwidth Reverse 1TPC - 3R2W RFO
MLC Remote Socket Peak bandwidth Reverse 1TPC - 1R1W RFO
MLC Remote Socket Peak bandwidth Reverse 1TPC - 100W
MLC Remote Socket Peak bandwidth Reverse 1TPC - 2R1W NTW
MLC Remote Socket Peak bandwidth Reverse 1TPC - 1R1W NTW
MLC Remote Socket Peak bandwidth Reverse 1TPC - 3R1W NTW
MLC Remote Socket Peak bandwidth Reverse 1TPC - 2R1W NTW (triad like)
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 1 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 2 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 4 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 8 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 12 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 16 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 20 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 24 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 28 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 32 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 36 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 40 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 44 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 48 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 52 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 56 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 60 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 64 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 68 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 72 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 76 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 80 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 84 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 88 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 92 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 96 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 100 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 104 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 108 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 112 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 116 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 120 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 124 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 128 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 132 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 136 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 140 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 144 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 148 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 152 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 156 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - 160 core
MLC Bandwidth Core Scaling - 1TPC Socket 0 100R - All core
MLC Loaded Latency 100R BW Inject Delay 0
MLC Loaded Latency 100R BW Inject Delay 2
MLC Loaded Latency 100R BW Inject Delay 8
MLC Loaded Latency 100R BW Inject Delay 15
MLC Loaded Latency 100R BW Inject Delay 50
MLC Loaded Latency 100R BW Inject Delay 100
MLC Loaded Latency 100R BW Inject Delay 200
MLC Loaded Latency 100R BW Inject Delay 300
MLC Loaded Latency 100R BW Inject Delay 400
MLC Loaded Latency 100R BW Inject Delay 500
MLC Loaded Latency 100R BW Inject Delay 700
MLC Loaded Latency 100R BW Inject Delay 1000
MLC Loaded Latency 100R BW Inject Delay 1300
MLC Loaded Latency 100R BW Inject Delay 1700
MLC Loaded Latency 100R BW Inject Delay 2500
MLC Loaded Latency 100R BW Inject Delay 3500
MLC Loaded Latency 100R BW Inject Delay 5000
MLC Loaded Latency 100R BW Inject Delay 9000
MLC Loaded Latency 100R BW Inject Delay 20000
MLC Loaded Latency 100R Latency Inject Delay 0
MLC Loaded Latency 100R Latency Inject Delay 2
MLC Loaded Latency 100R Latency Inject Delay 8
MLC Loaded Latency 100R Latency Inject Delay 15
MLC Loaded Latency 100R Latency Inject Delay 50
MLC Loaded Latency 100R Latency Inject Delay 100
MLC Loaded Latency 100R Latency Inject Delay 200
MLC Loaded Latency 100R Latency Inject Delay 300
MLC Loaded Latency 100R Latency Inject Delay 400
MLC Loaded Latency 100R Latency Inject Delay 500
MLC Loaded Latency 100R Latency Inject Delay 700
MLC Loaded Latency 100R Latency Inject Delay 1000
MLC Loaded Latency 100R Latency Inject Delay 1300
MLC Loaded Latency 100R Latency Inject Delay 1700
MLC Loaded Latency 100R Latency Inject Delay 2500
MLC Loaded Latency 100R Latency Inject Delay 3500
MLC Loaded Latency 100R Latency Inject Delay 5000
MLC Loaded Latency 100R Latency Inject Delay 9000
MLC Loaded Latency 100R Latency Inject Delay 20000
SPEC2017_fp_rate (score)
SPEC2017_int_rate (score)
Copy Bandwidth (NTW) (MB/s)
Scale Bandwidth (NTW) (MB/s)
Add Bandwidth (NTW) (MB/s)
Triad Bandwidth (NTW) (MB/s)

## DPMO？
ID | Title | Category | Priority | Config | Test Schedule | Test Result | Sighting | Test owner | Test Duration | Test Date | Test Config | Comment | hrs | days
| Platform-stability-G3_Cycling | Stability | P1 | 1DPC | WW27 | Pass |  | Zhou, Jun1X | 3051 | 2024-07-01 | 801028 | 7/1 20:20 500 cycles complete 7/17 17:00 rerun-1000 1000 cycles complete 6,136 minutes | 50.85 | 2.1187 | 4.2
| Platform-stability-S5_Cycling | Stability | P1 | 1DPC | WW28 | Pass |  | Zhou, Jun1X | 2542 | 2024-07-05 | 801028 | 7/5 14:40 500 cycles complete 7/22 11:30 rerun-1000 1000 cycles complete 5,073 minutes | 42.3667 | 1.7653 | 3.5
| Platform-stability-Warmreset_Cycling | Stability | P1 | 1DPC | WW29 | Pass |  | Zhou, Jun1X | 1600 | 2024-07-03 | 801028 | 7/3 9:00 500 cycles complete 7/26 9:00 rerun-1000 1000 cycles complete 3,202 minutes | 26.6667 | 1.1111 | 2.2
| Platform-stability-G3_Cycling | Stability | P1 | 2DPC | WW30 | Pass |  | Zhou, Jun1X | 3257 | 2024-07-05 | 801016 | 7/5 8:00 500 cycles complete 7/12 15:00 rerun-1000 1000 cycles complete 6,537 minutes | 54.2833 | 2.2618 | 4.5396
| Platform-stability-S5_Cycling | Stability | P1 | 2DPC | WW31 | Pass |  | Zhou, Jun1X | 2698 | 2024-07-02 | 801016 | 7/2 15:30 500 cycles complete 7/8 10:00 rerun-1000 1000 cycles complete 5,413 minutes | 44.9667 | 1.8736 | 3.759
| Platform-stability-Warmreset_Cycling | Stability | P1 | 2DPC | WW32 | Pass |  | Zhou, Jun1X | 1710 | 2024-07-03 | 801016 | 7/3 13:30 500 cycles complete 7/17 15:30 rerun-1000 1000 cycles complete 3,438 minutes | 28.5 | 1.1875 | 2.3

## PnP(speccpu-detail)？
Golden_Sample_H-64GB | [6 empty] | CXSH SKU1 64GB RevA
[5 empty] | median | %CV |  |  |  | median | %CV | difference
INT | 500.perlbench_r | 714.97 | 714.33 | 718.35 | 714.97 | 0.2464% | 723.46 | 715.65 | 718.58 | 718.58 | 0.4479% | 0.5049%
| 502.gcc_r | 787.01 | 786.35 | 786.63 | 786.63 | 0.03438% | 785.28 | 784.18 | 786.58 | 785.28 | 0.1249% | -0.1716%
| 505.mcf_r | 1447.48 | 1445.53 | 1444.58 | 1445.53 | 0.08349% | 1445.99 | 1442.42 | 1443.68 | 1443.68 | 0.1024% | -0.128%
| 520.omnetpp_r | 604.71 | 606.9 | 606.01 | 606.01 | 0.1484% | 604.94 | 606.15 | 606.21 | 606.15 | 0.09658% | 0.0231%
| 523.xalancbmk_r | 1288.63 | 1285.51 | 1288.19 | 1288.19 | 0.1071% | 1291.45 | 1292.54 | 1291.64 | 1291.64 | 0.0368% | 0.2678%
| 525.x264_r | 1971.43 | 1973.1 | 1970.79 | 1971.43 | 0.04939% | 1974.85 | 1974.22 | 1973.45 | 1974.22 | 0.029% | 0.1415%
| 531.deepsjeng_r | 724.26 | 726.93 | 726.82 | 726.82 | 0.1699% | 727.36 | 727.13 | 727.41 | 727.36 | 0.01676% | 0.0743%
| 541.leela_r | 718.82 | 719.74 | 717.26 | 718.82 | 0.1424% | 718.64 | 719.42 | 718.91 | 718.91 | 0.04498% | 0.01252%
| 548.exchange2_r | 2179.5 | 2179.3 | 2169.35 | 2179.3 | 0.2177% | 2153.16 | 2181.99 | 2187.82 | 2181.99 | 0.6969% | 0.1234%
| 557.xz_r | 499.83 | 493.47 | 492.65 | 493.47 | 0.6479% | 492.82 | 493.98 | 493.56 | 493.56 | 0.09718% | 0.01824%
| GEOMEAN | 966.28 | 965.41 | 964.92 | 965.41 | 0.05825% | 965.3735 | 965.7805 | 966.6038 | 965.7805 | 0.05298% | 0.03838%
FP | 503.bwaves_r | 4644.58 | 4646.09 | 4646.22 | 4646.09 | 0.01602% | 4636.82 | 4642.53 | 4645.08 | 4642.53 | 0.0744% | -0.07662%
| 507.cactuBSSN_r | 1175.09 | 1186.51 | 1190.76 | 1186.51 | 0.5588% | 1189.71 | 1189.02 | 1187.65 | 1189.02 | 0.07202% | 0.2115%
| 508.namd_r | 762.53 | 760.86 | 764.26 | 762.53 | 0.182% | 759.91 | 761 | 763.54 | 761 | 0.1997% | -0.2006%
| 510.parest_r | 668.82 | 667.7 | 668.1 | 668.1 | 0.06935% | 668.25 | 668.02 | 667.67 | 668.02 | 0.0357% | -0.01197%
| 511.povray_r | 1162.97 | 1169.6 | 1155.08 | 1162.97 | 0.5105% | 1161.67 | 1162.64 | 1161.18 | 1161.67 | 0.05222% | -0.1118%
| 519.lbm_r | 436.18 | 436.37 | 436.32 | 436.32 | 0.01843% | 435.96 | 435.05 | 435.87 | 435.87 | 0.09398% | -0.1031%
| 521.wrf_r | 758.94 | 757.76 | 758.18 | 758.18 | 0.0644% | 757.49 | 757.72 | 757.56 | 757.56 | 0.01271% | -0.08177%
| 526.blender_r | 1106.61 | 1104.52 | 1104.8 | 1104.8 | 0.08381% | 1105.63 | 1108.21 | 1107.57 | 1107.57 | 0.09908% | 0.2507%
| 527.cam4_r | 1208.04 | 1209.87 | 1209.48 | 1209.48 | 0.06509% | 1209.14 | 1210.36 | 1216.57 | 1210.36 | 0.2684% | 0.07276%
| 538.imagick_r | 3260.16 | 3269.95 | 3229.01 | 3260.16 | 0.5366% | 3254.37 | 3270.21 | 3261.31 | 3261.31 | 0.1987% | 0.03527%
| 544.nab_r | 1916.76 | 1915.38 | 1916.41 | 1916.41 | 0.03057% | 1920.71 | 1907.59 | 1914.37 | 1914.37 | 0.2799% | -0.1064%
| 549.fotonik3d_r | 621.7 | 621.83 | 622.12 | 621.83 | 0.02823% | 621.12 | 621.03 | 621.79 | 621.12 | 0.05457% | -0.1142%
| 554.roms_r | 469.47 | 471.23 | 470.86 | 470.86 | 0.161% | 471.34 | 470.63 | 471.32 | 471.32 | 0.07007% | 0.09769%
| GEOMEAN | 1076.67 | 1078.05 | 1076.73 | 1076.73 | 0.05913% | 1077.19 | 1077.23 | 1078.11 | 1077.23 | 0.0394% | 0.04644%

## At Scale-Cluster Test
workload | Domain Category | Memory Config | Test Schedule | Test Result | Sighting | Test owner | Test Date | Test Config | Comment
system-idle | System | 1DPC
imc-external | Memory | 1DPC
passmark-burnin | System | 1DPC
passmark-burnin-vm | System | 1DPC
mss-mlc | Memory | 1DPC
sandstone-latest | System | 1DPC
unified_hvm_unified_v4 |  | 1DPC
nightly |  | 1DPC
sap-hana/sf10 |  | 1DPC
sap-hana/sf100 |  | 1DPC
pts - cachebench | System | 1DPC
pts - memory | Memory | 1DPC
Genie Mixmode |  | 1DPC
Genie Linpack |  | 1DPC
Genie Omnetpp |  | 1DPC
Genie iMunch |  | 1DPC
Genie Gromacs |  | 1DPC
Genie Povray |  | 1DPC
Genie HPCG |  | 1DPC
Genie FIO |  | 1DPC
Genie Ycruncher |  | 1DPC
Genie Gemmbench |  | 1DPC
Genie Stressng |  | 1DPC
Genie MLC |  | 1DPC
Resnet50 amx | System | 1DPC
Resnet50 Legacy 1.0 | System | 1DPC
SF Benchdnn | System | 1DPC
spec17 | System | 1DPC
stream | Memory | 1DPC
unixbench | System | 1DPC
GeekBench | System | 1DPC
PATA-Memory Read Test | Memory | 1DPC
PTAT-Memory Write Test | Memory | 1DPC
PTAT-Memory Read/Write Test | Memory | 1DPC
vc-stressapp-mem-cpu-stress | System | 1DPC
vc-stressapp-mem-copy | Memory | 1DPC
vc-stressapp-mem-local-numa | Memory | 1DPC
vc-stressapp-mem-remote-numa | Memory | 1DPC
vc-prime95 | System | 1DPC
vc-coremark | System | 1DPC
vc-coremarkpro | System | 1DPC
vc-aspnet | System | 1DPC
opendcdiag |  | 1DPC
perf-bench-mem-all | System | 1DPC
perf-bench-numa-all | System | 1DPC
spiv-ipu-dogwoods-burnin-mlc-verw-streeor-v1.6 | System | 1DPC
contextswitch | System | 1DPC
cyclictest | System | 1DPC
hackbench | System | 1DPC
mlc | Memory | 1DPC
specjbb |  | 1DPC
solar |  | 1DPC
spin |  | 1DPC
SpecPower |  | 1DPC
At Scale - Warm Cycling 200 cycles | System | 1DPC
At Scale - Cold Cycling 200 cycles | System | 1DPC
At Scale - AC Cycling 200 cycles | System | 1DPC
At Scale - Warm Cycling with SGX enabling 100 cycles | System | 1DPC
At Scale - Cold Cycling SGX enabling 100 cycles | System | 1DPC
At Scale - AC Cycling SGX enabling 100 cycles | System | 1DPC
system-idle |  | 2DPC
imc-external |  | 2DPC
passmark-burnin |  | 2DPC
passmark-burnin-vm |  | 2DPC
mss-mlc |  | 2DPC
sandstone-latest |  | 2DPC
unified_hvm_unified_v4 |  | 2DPC
nightly |  | 2DPC
sap-hana/sf10 |  | 2DPC
sap-hana/sf100 |  | 2DPC
pts - cachebench |  | 2DPC
pts - memory |  | 2DPC
Genie Mixmode |  | 2DPC
Genie Linpack |  | 2DPC
Genie Omnetpp |  | 2DPC
Genie iMunch |  | 2DPC
Genie Gromacs |  | 2DPC
Genie Povray |  | 2DPC
Genie HPCG |  | 2DPC
Genie FIO |  | 2DPC
Genie Ycruncher |  | 2DPC
Genie Gemmbench |  | 2DPC
Genie Stressng |  | 2DPC
Genie MLC |  | 2DPC
Resnet50 amx |  | 2DPC
Resnet50 Legacy 1.0 |  | 2DPC
SF Benchdnn |  | 2DPC
spec17 |  | 2DPC
stream |  | 2DPC
unixbench |  | 2DPC
GeekBench |  | 2DPC
PATA-Memory Read Test |  | 2DPC
PTAT-Memory Write Test |  | 2DPC
PTAT-Memory Read/Write Test |  | 2DPC
vc-stressapp-mem-cpu-stress |  | 2DPC
vc-stressapp-mem-copy |  | 2DPC
vc-stressapp-mem-local-numa |  | 2DPC
vc-stressapp-mem-remote-numa |  | 2DPC
vc-prime95 |  | 2DPC
vc-coremark |  | 2DPC
vc-coremarkpro |  | 2DPC
vc-aspnet |  | 2DPC
opendcdiag |  | 2DPC
perf-bench-mem-all |  | 2DPC
perf-bench-numa-all |  | 2DPC
spiv-ipu-dogwoods-burnin-mlc-verw-streeor-v1.6 |  | 2DPC
contextswitch |  | 2DPC
cyclictest |  | 2DPC
hackbench |  | 2DPC
mlc |  | 2DPC
specjbb |  | 2DPC
solar |  | 2DPC
spin |  | 2DPC
SpecPower |  | 2DPC
At Scale - Warm Cycling 200 cycles |  | 2DPC
At Scale - Cold Cycling 200 cycles |  | 2DPC
At Scale - AC Cycling 200 cycles |  | 2DPC
At Scale - Warm Cycling with SGX enabling 100 cycles |  | 2DPC
At Scale - Cold Cycling SGX enabling 100 cycles |  | 2DPC
At Scale - AC Cycling SGX enabling 100 cycles |  | 2DPC

## HWV？
Test Cases | Config. | Test Schedule | Test Result | Sighting | Comment
MVL - 4C Stress - LVLT | 1DPC
MVL - 4C Stress - LVHT | 1DPC
MVL - 4C Stress - HVLT | 1DPC
MVL - 4C Stress - HVHT | 1DPC
MVL - 4C Power Cycling - LVLT | 1DPC
MVL - 4C Power Cycling - LVHT | 1DPC
MVL - 4C Power Cycling - HVLT | 1DPC
MVL - 4C Power Cycling - HVHT | 1DPC
StressNG - LV - BCRH | 1DPC
StressNG - HV - BHRC | 1DPC
StressNG - LV - BCRH | 2DPC
StressNG - HV - BHRC | 2DPC